## Sheet1
Tower | Tracks | Total Stories | E2E Required | E2E Required Blank | Proposed | Solution/Product Analysis | Ready for Grooming | With SDET | With Dev | With E2E | E2E Completed | Moved to UAT | High Sev Defects | Total Open Defects | Status
Case Mgmt & KMT | Case Collaboration | 46 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 2 | AMBER
| Case creation and Management | 73 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 31 | 31 | 0 | 3 | AMBER
| GBS Care | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | AMBER
| Case Initiation & Routing | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | GREEN
| KMT | 42 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 3 | AMBER
| Delta | 39 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 23 | 23 | 3 | 4 | AMBER
| Grand Total | 208 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 110 | 110 | 4 | 13
Tower | Tracks | Total Stories | E2E Required | E2E Required Blank | Proposed | Solution/Product Analysis | Ready for Grooming | With SDET | With Dev | With E2E | E2E Completed | Moved to UAT | High Sev Defects | Total Open Defects | Status
Contact Channels & Exception Management | Chat | 24 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 1 | 2 | AMBER
| GBS Care - Chat | 16 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | GREEN
| Voice | 13 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | GREEN
| Grand Total | 53 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 43 | 1 | 2
Tower | Tracks | Total Stories | E2E Required | E2E Required Blank | Proposed | Solution/Product Analysis | Ready for Grooming | With SDET | With Dev | With E2E | E2E Completed | Moved to UAT | High Sev Defects | Total Open Defects | Status
Data Insights, Integration and Security | Data Migration | 13 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 5 | 0 | 0 | GREEN
| Integration | 11 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | GREEN
| Analytics | 18 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | GREEN
| Security | 26 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | GREEN
| Grand Total | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 27 | 27 | 0 | 0